Background

The Eastern Mental Health Service Coordination Alliance (EMHSCA) Strategic Planning Subcommittee (SP SC) was formed in October 2013.

The initial purpose of the Subcommittee was to inform and support the development of the EMHSCA strategic plan. As the EMHSCA strategic plan is finalised further work has been proposed for this subcommittee and is outlined in this work plan.

At the SP SC meeting held on the 16th June 2014 the subcommittee identified the key areas that are related to the EMHSCA strategic plan and require further work.  These included:

- Surveying EMHSCA members regarding their current satisfaction with the Alliance and their organisations future needs.

- Reviewing EMHSCA committee membership with regard to the recent AOD and MH reforms.

- Updating current EMHSCA MOU to line up with the strategic plan and membership review.

- Establishing connections between existing local Consumer and Carer advisory groups and improving pathways to EMHSCA.

EHMSCA  -  “Creating opportunities to work strategically across the region with multi-sectoral partners”

Completed work October 2013-December 2014

- Survey of EMHSCA members re Shared Agenda items.

- Development of Vision statement and tag.

- Development of Values statements.

- SWOT analysis of EMHSCA.

- Development of the EMHSCA strategic plan 2014-2016.

- Review of EMHSCA Membership.

- Commenced linking of Consumer and Carer advisory groups.

- Created EMHSCA Measures Matrix to align with Strategic Plan.

Completed work for 2015

- Developed and implemented EMHSCA Quality & Strategy survey and provided feedback to EMHSCA.

- Developed and implemented Partnership survey

- EMHSCA MOU was reviewed and revised for resigning in 2016.

- Communications guide was developed and website repository updated.

- Support was provided for the  establishment of the Eastern Peer Support Network.

Completed work for 2016

1. Facilitated review of EMHSCA MOU and resigning.

2. Reviewed and revised the EMHSCA Strategic Plan.

3. Supported peer and service engagement with Eastern Peer Support Network activities.

4. Monitored EMHSCA membership and supported strategic expansion.

Planned work for 2017

- Develop  strategy to maintain linkages and collaboration during the roll-out of NDIS in this region.

- Develop clear objectives regarding Physical Health and Mental Health and facilitate new work within the EMHSCA structure.

- Consider useful links and improvements to the EMHSCA structure to promote collaborative work with Aboriginal Services.

- Consider ways to strengthen screening and pathways to support for people experiencing Family Violence.

- Support peer and service engagement with Eastern Peer Support Network activities.

Monitor EMHSCA membership and support strategic expansion.

| Strategies | Actions | Status / Deliverable | Timeline | Responsibility |
| --- | --- | --- | --- | --- |
| Preserve local partnerships and collaborative arrangements whilst MHCSS transitions to NDIS | Support provision of NDIS forum |  | June - 31st August 2017 | EMHSCA WD SC/ SP SC/ EMPHN |
|  | Create entry point for EMHSCA partner feedback to relevant bodies |  | Aug-Nov 2017 | SP SC |
|  | Examine partnerships in relation to NDIS |  | Aug- Nov 2017 | SP SC |
|  | Map services provided by EMHSCA partners –NDIS and non-NDIS |  | Aug-Nov 2017 | SP SC |
|  | Gather evidence to enable EMHSCA to have collective impact |  | Ongoing | SP SC |
|  | Create NDIS info area on EMHSCA shared repository |  | September 2017 | EMHSCA PO |
| Success Indicator: People experiencing mental ill health and/or substance use issues are receiving integrated and collaborative services in this region. |
| Develop clear objectives regarding Physical Health and Mental Health and facilitate new work within the EMHSCA structure. | Gather data re issues regarding PH support for people with Mental ill health |  | Feb 2017 | SP SC & project officer |
|  | Consider any issues raised from data. |  | March 2017 |  |
|  | Consult with consumer and carer groups |  | March/ April/May | Jacky Close & EMHSCA PO |
|  | Consider results of consultation |  | April/May | SP SC & Jacky Close |
|  | Co-design of PH 4 MH project |  | TBA | Jacky Close and DDCCAC |
|  | Report back to EMHSCA committee |  | TBA | Jacky Close and DDCCAC |
| Success Indicator: Improved understanding of the needs of staff in the EMR in relation to PH for MH - to inform the work going forwards.. |
| Improve collaboration and enhance relationships with Aboriginal services. | Consider proposal to create communication relationship for EMHSCA with Aboriginal services. |  | November 2016 | Chelsea Brand and SP SC |
|  | Provide recommendations to EMHSCA committee for consideration and endorsement |  | December 2017 | SP SC Chair |
|  | Engage new Aboriginal Engagement Manager at DHHS. |  | March 2017 | EMHSCA PO |
|  | Develop brief guide to enhancing relationships with Aboriginal services in consultation with local Aboriginal leaders. |  | July 2017 | SP SC & PO |
|  | Present guide for endorsement to EMHSCA committee |  | August 2017 | SP SC Chair |
|  | Provide final guide to EMHSCA |  | September 2017 | PO |
| Success Indicator: Improvement to number of aboriginal people accessing mainstream services in the EMR. |
| Strengthen screening and pathways to support for people experiencing Family Violence. | Examine any existing data regarding the needs of staff from EMHSCA services in relation to working with Family Violence issues. |  | August 2017 | SP SC |
|  | Provide recommendations to the EMHSCA committee in relation to effective capacity building activities and collaborative partnerships. |  | October 2017 | SP SC |
| Success Indicator: |
| Ensure EMHSCA membership is appropriate and strategic | Consider requests for EMHSCA committee membership and present to EMHSCA |  | Ongoing | SP SC |
|  | Review Membership to line up with EMHSCA strategic plan |  | March 2017 | SP SC |
|  | Discuss EMHSCA committee membership requests at EMHSCA committee meetings |  | Ongoing | SP SC & EMHSCA |
|  | Provide updates regarding subcommittee attendance and membership to the EMHSCA committee |  | June and December | Project officer |
| Success indicator: EMHSCA committee members attend meetings regularly and make valuable contributions to the Alliance. |
| Support establishment of Peer Support Network in EMR | Provide initial support to project as it is establishing. |  | July- Sept. 2015 | SP SC |
|  | Provide updated information to project coordinator regarding peer advisors, workers and consultants in EMHSCA services. |  | March 2017 | SP SC and EMHSCA members |
|  | Offer suitable venues for PSN meetings via EMHSCA member services |  | November 2017 | SP SC, EMHSCA members |
|  | Host meetings at EMHSCA member services |  | July 2016-August 2017 | SP SC members and EMHSCA service reps. |
|  | Participate in project surveys and events |  | When required | SP SC |
| Success Indicator: Peer Support Network is established in the EMR and involves relevant EMHSCA services. |

|  | Not Started |  | Delayed |  | On track |  | Completed |
| --- | --- | --- | --- | --- | --- | --- | --- |