Background

The Eastern Mental Health Service Coordination Alliance (EMHSCA) Collaborative Pathways Sub committee (CP SC) was formed in December 2012.

The purpose of the Subcommittee is to explore how member agencies can work together to improve the holistic health outcomes for people with mental health and co-occurring concerns by supporting the development and implementation of shared protocols and documentation within and between member agencies.

This work plan outlines the strategies and activities that the subcommittee identified and agreed to work on at their planning sessions from December 2012.

At the planning meetings the subcommittee identified the key issues that are contributing to less than optimum integrated, person centered, recovery focused care for people with mental health problems.  These included:

- Current Partnership & Collaboration Protocol lacks flexibility for application to a wider variety of service providers thus inhibiting a collaborative approach to care planning

- Service providers are not necessarily aware of the Partnership & Collaboration protocol that exists

- Information sharing issues – What do we share with whom and how? What is the most ideal format for information sharing?

- Shared Care plan (existing T/IRP) is strongly clinical in focus – not person centered/ recovery focused language

- Some agencies have their own care plans

- Someone needs to drive the implementation of shared care protocols in each organisation

Agreed Vision

“All participating agencies offer opportunities for people to participate in a person centered, integrated, shared care plan with a recovery focus.”

Completed Work 2013

- Review of Eastern MH Alliance Shared Care Protocol

- Consultation with Dual Diagnosis Consumer and Carer Advisory Council re existing shared care practices and documents

- Development of new Shared Care Practices and Collaborative Planning Protocol

- Re development of regional Individual Recovery Plan

- Development of audit in relation to existing shared care practices at EMHSCA member services who are involved in shared care

Completed Work for 2014

- Development of an implementation strategy in relation to the Shared Care Practices and Collaborative Planning Protocol for EMHSCA member services.

- Development of the Service Coordination Champion role across EMHSCA member services to assist with implementation of the Shared Care Practices and Collaborative Planning Protocol.

- Relationship developed between Dual Diagnosis Linkages and EMHSCA to support Service Coordination Champion role.

- Collection and evaluation of base-line data regarding Shared care practices in the EMR.

Completed work for 2015

- Conducted follow up Shared Care audit and provide feedback to EMHSCA services.

- Supported development and implementation of Consumer Shared care survey.

- Surveyed EMHSCA services regarding implementation of Shared Care protocol.

- Continued to work together with the Workforce Development Committee to build capacity of organisations regarding Shared Care planning and associated activities.

- Supported establishment of Service Coordination Champion role in the EMR.

- Reviewed Shared Care Practices and Collaborative Planning Protocol.

Completed work for 2016

- Disseminate results of Consumer Shared Care Survey and provide recommendations for future Consumer surveys.

- Conduct Annual Shared Care audit and provide feedback to EMHSCA services.

- Clarify further the Service Coordination Champion role in the EMR.

- Development of Co-location map.

Agreed Strategies for 2017

- Initiate new Consumer Shared Care Survey in line with Shared Care Audit.

- Review Shared Care Protocol in relation to EMHSCA’s new cohort focused agenda.

- Conduct Annual Shared Care audit and provide feedback to EMHSCA services.

- Continue to work together with the Workforce Development Committee to build capacity of organisations regarding Shared Care planning and associated activities.

- Support further development of Service Coordination Champion role in the EMR.

- Develop Co-location guide.

- Support EMHSCA services to implement the EMHSCA Shared care protocol locally.

- Redevelop the EMHSCA Shared Care Plan template.

- Articulate EMHSCA’s role in supporting referral pathways

| Strategies | Actions | Status / Deliverable | Timeline | Responsibility |
| --- | --- | --- | --- | --- |
| Monitor regional shared care practices. | Redevelop Shared Care Audit guide |  | January 2017 | CP SC |
|  | Circulate audit documents to EMHSCA services |  | February 2017 | Project Officer |
|  | Support Audit with information and discussion at EMHSCA meetings |  | Feb & April 2017 | Project Officer |
|  | Collect data from EMHCSA member services involved in shared care practices |  | End May 2017 | Project Officer |
|  | Provide feedback to EMHSCA re collated Shared Care Audit data and compare annual results |  | August 2017 | CP SC and Project Officer |
|  | Develop survey of EMHSCA members re Shared Care audit satisfaction |  | September 2017 | CP SC |
|  | Conduct survey of EMHSCA members involved in audit regarding their satisfaction |  | October 2017 | CP SC |
| Success indicators: All EMHSCA services involved in Shared Care Practices provide snapshot data. |
| Support and Monitor Consumer Shared Care Survey | Develop Consumer survey to support Shared care audit |  | January/ February 2017 | CPSC and Project Officer |
|  | Provide proposed Consumer Care Planning Survey questions to Consumer & Carer Advisory groups for their input |  | March/April 2017 | CPSC and Project Officer |
|  | Develop Consumer Care Planning Survey implementation strategy and time line |  | June 2017 | CPSC and Project Officer |
|  | Provide final version of Consumer Shared Care Survey (CSCS) Guide to EMHSCA members including dates for commencement |  | August 2017 | CPSC |
|  | Develop training session for Peer survey providers |  | July 2017 | CPSC |
|  | Provide training session for Peer survey providers |  | September 2017 | CPSC |
|  | Follow up collection of results from EMHSCA members |  | November 2017 | Project Officer |
|  | Collate results of survey |  | December 2017 |  |
|  | Provide Summary of survey results to EMHSCA members |  | February 2018 | Project officer |
|  | Develop satisfaction survey for EMHSCA members re CSCS |  | March 2018 | CP SC |
| Success Indicators: Consumers of EMHSCA services involved in the Shared Care audit provide their perspective regarding shared care practices. |
| Improve and enhance Shared Care Practices | Review and revise EMHSCA IRP template 2013 |  | Feb/March 2017 | CP SC |
|  | Develop brief and guide for EMHSCA re Shared Care Planning template |  | April/May 2017 | CP SC |
|  | Present Shared Care Planning Template to EMHSCA for endorsement |  | June 2017 | Project officer |
|  | Add to Shared Care Protocol Implementation Strategy |  | November 2017 | CP SC |
| Success Indicators: EMHSCA services adopt the Shared Care Planning proforma |
| Provide ongoing support to Linkages and Service Coordination Champion role in EMR. | Support establishment of Linkage Calendar |  | November 2016 | CP SC & EDDS |
|  | Review Linkage Terms of reference |  | June 2017 | CP SC & EDDS |
|  | Evaluate outcomes of EMR Linkages |  | June 2017 | CP SC & EDDS |
|  | Provide leadership within each EMHSCA service as Service Coordination Champions |  | Ongoing | CPSC members |
| Success Indicator: Local linkages and the Service Coordination Champion Role are supported and sustained. |
| Support EMHSCA services to implement the EMHSCA Shared care protocol locally. | Review 2015 Implementation Questionnaire. |  | October 2017 | CP SC |
|  | Revise Implementation guide. |  | November 2017 | Project Officer |
|  | Provide draft to EMHSCA committee for endorsement |  | February 2018 | Project officer |
|  | Provide final version of Implementation guide to EMHSCA |  | April 2018 | CP SC; Project officer |
| Success Indicator: EMHSCA services utilize the Shred Care Protocol implementation Guide to improve shared care practices across their services. |
| 6. Support improved integration of service provision. | Map current colocation arrangements |  | November 2016 | CP SC |
|  | Discuss key aspects of colocation and challenges |  | November2016 | CP SC |
|  | Develop draft colocation guide |  | February 2017 | CP SC |
|  | Develop final draft and present to EMHSCA for endorsement |  | June 2017 | CP SC ; Project officer |
|  | Circulate final document to EMHSCA members and seek final endorsement |  | August 2017 | CP SC ; Project officer |
|  | Provide guide to the Workforce Development (WD) Subcommittee to include in WD events. |  | September 2017 | Project officer; WD SC |
| Success Indicator: There is an increase in effective service colocation in the EMR |
| 7. Ensure currency and consistency of information provided by EMHSCA regarding principles of shared care in the EMR. | Review EMHSCA Shared Care Protocol in relation to new cohort focused agenda |  | July/August 2017 | CP SC |
|  | Develop draft of recommended changes |  | September 2017 | CP SC |
|  | Consult with all EMHSCA member service leaders regarding recommendations |  | October 2017 | Project officer |
|  | Develop final draft and present to EMHSCA for ratification |  | December 2017 | CP SC ; Project officer |
|  | Circulate Final revised Shared Care Protocol to EMSHCA |  | February 2017 | Project officer |
|  | Provide revised Shared Care Protocol to participants at EMHSCA workshop |  | March 2017 | Project officer; WD SC |
| Success Indicator: The EMHSCA Shared Care Protocol reflects the EMHSCA cohort focused agenda to support good practice across local health and community services. |

|  | Not Started |  | Delayed |  | On track |  | Completed |
| --- | --- | --- | --- | --- | --- | --- | --- |